## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
|  | 1 | Foundations required for doing project
|  | 2 | LLM for Contract analysis
|  | 3 | Clause Identification and Risk Analysis Engine
|  | 4 | Update tracking and Contract Modification

## Sprint Backlog
]
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | DDd
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
1 |  | Foundations required for doing project | Nov 10th | Nov 24th | Tanishq Navsariwala | Learnt about fundamentals required for project | Done |  | Inroductory Session | Installation of Python and Jupyter Notebook | Learned Naming Conventions and Python Keywords | Learned about Variables and how to operate on the agile sheet | Multi Variables and Datatypes | Practiced all previous session topics | practiced all topics covered in previous session | learnt about range(),mutable & immutable, control statements | Flow controls and functions | Learnt about Functions with return keyword, arguments and types | learnt about modules and Keywords | learnt about oops concept | constructors and instance variables | revision
2 |  | LLM For Contract Analysis | Nov 25th | Dec 9th | Tanishq Navsariwala | Understood about the project, LLM and Executed Demo codes | Done |  | Overview of The Project | Presentation about Project understanding | Virtual Environment Creation | Introduction to Tech Tools | Presentation Session #2 | Revised Concepts about Python | Revised OOPS | Overview of Prompt Engineering | LLM Fundamentals | LLM Fundamentals and Groq API key | Explanation and Execution of Demo codes | Introduction to Packages | Revised | Revised Packages
3 |  | Clause Detection & Risk Analysis Engine | Dec 10th | Dec 24th | Tanishq Navsariwala | Understood clause extraction and risk analysis with some sample contracts | Done |  | Overview about workflow and Project Structure | Overview about workflow and Project Structure | Text Extraction and Overlapping | Introduction to Clause Identification | Discussed Clause Extraction | Revised the topics covered this week | Revised the topics covered this week | Discussed about the assignment and cleared the queries of the team members | Risk Analysis Engine | Discussed run and pipeline Codes, Intro for Regulatory Update Tracking | Practised milestone 1 and milestone 2 | Regulatory Update Tracking | Worked on assignment | Worked on assignment
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 22nd | Jan 8th | Tanishq Navsariwala | Understood Regulatory Update Tracking System and Contract Modification with codes | Done |  | Assignment Practice | Discussed about Assignment Progress | Regulatory Update Tracking and related information | Studied about regulatory update Tracking System and Assignment presentation | Executed demo 2 & 3 codes and completed "building the regulatory update tracking" | Previous topics Revision | Practiced milestone-3 demo codes | Contract Modification and Ammendment Engine | Milestone 3 Topics Revision | Milestone 3 Implementation | Milestone 3 Revision | FeedParser and Milestone 3 Execution | Slack Integration | revision

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7